## Schedule of Works
Construction of Sport Hall and Swimming Pool in Poti
Schedule of Works
Item | Description | Months
|  | I |  |  | II |  |  | III |  |  | IV |  |  | V |  |  | VI |  |  | VII |  |  | VIII |  |  | IX |  |  | X |  |  | XI |  |  | XII
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
I. Surveys and Design
1 | Detailed topography survey of the complete site
2 | Detailed geological survey for design and construction
3 | Allow for obtaining of approvals and permits
4 | Detailed design for the Sport Hall
5 | Detailed design for the Swimming pool
II. Construction of Sport Hall
6 | Mobilization
7 | Site preparation & temporary site facilities
8 | Civil Works
9 | Earthworks
10 | Foundations
11 | Concrete and r/concrete works
12 | Steel structures
13 | Floors
14 | Windows and doors
15 | Roofing
16 | Internal finishes
17 | External Finishes
18 | Mechanical Installations
19 | Electrical Installations
20 | Installation of Equipment
21 | Internal water and sanitation systems
22 | HAVC
23 | External water and sewage systems
24 | Landscaping/parking areas
25 | Drainage and storm water systems
26 | Tests on completion, commissioning, start-up
27 | Operation & maintenance concept, manuals
28 | As-build documentation and drawings
29 | External gas supply
30 | External Power Supply
III. Construction of Swimming pool
31 | Mobilization
32 | Site preparation & temporary site facilities
33 | Civil Works
34 | Earthworks
35 | Foundations
36 | Concrete and r/concrete works
37 | Steel structures
38 | Floors
39 | Windows and doors
40 | Roofing
41 | Internal finishes
42 | External Finishes
43 | Mechanical Installations
44 | Electrical Installations
45 | Installation of Equipment
46 | Internal water and sanitation systems
47 | HAVC
48 | External water and sewage systems
49 | Landscaping/parking areas
50 | Drainage and storm water systems
51 | Tests on completion, commissioning, start-up
52 | Operation & maintenance concept, manuals
53 | As-build documentation and drawings
54 | External gas supply
55 | External Power Supply