## Work Schedule
Rehabilitation of Bolnisi and Tsalka Water Supply Systems
Work Schedule
N | Description | Months
|  | I |  |  | II |  |  | III |  |  | IV |  |  | V |  |  | VI |  |  | VII |  |  | VIII
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
I. Bolnisi WS System
1 | MOS Chlorination System and electrical distribution booard
2 | External Water Supply Network
3 | External Sewer System
4 | Reservoir Area "Communication" Pipelines
5 | Flow Meter Chamber & Air Valve Chamber
6 | Valve chambers
7 | RESERVOIRS REHABILITATION
8 | SCADA
II. Tsalka WS System
1 | 500 m3 Reservoir Civil Works;
2 | Reservoir Piping;
3 | Pipeline connections;
4 | Construction of Guard House;
5 | Chlorination Building & Equipment;
6 | Electrical Equipment & PLC;
7 | Calcium Hypochlorite – Ca(OCl)2 – Dosing Station & SCADA System;
8 | Reservoir Territory Lighting;
9 | Site Security Fence;
10 | Connection of reservoir Inlet Pipes and Outler Pipes to Existing D300mm & D250mm Steel Pipes;
11 | Arrangement of flow meter chamber;